DAILY FIELD REPORT - 07-07-2026

Project: Morena Conveyance Northern
Resident Engineer: Terry West
Weather: High: 71°°F, Low: 55°°F, Wind: 2-4 MPH NW, Clear, Overcast, Partly Cloudy
Hours: 06:30 - 15:00

General Notes:

RJ Noble focused on the outside lanes from town centre gateway to Noble on town centre dr. Started the evening with several cars parked in the no parking zone, PD was called; however, they didnt show up for several hours and before they could all the cars were moved so no cars had to be towed tonight. RJ Noble did have to skip a section about 80 ft long and a car width wide just south of town centre gateway but they got it on the way back up.

## Activities Detail

Town Centre - RJ Noble - Grind and Overlay

• Grind & Overlay — Wednesday, July 8, 2026:

- NB INSIDE TOWN CENTER — 31,701 SF (594 tons)

- CENTER LANES EXECUTIVE — 32,000 SF (600 tons)

Total: 63,701 SF / 1,194 Tons

• Material: 1460 TONS 1/2" FIBER MIX ID#21242163F

• Plant: MM LAKESIDE

• Material: GRINDS TO MIRAMAR

• Asphalt Laid: 1513.42 tons

• Traffic Control: WORK DESCRIPTION:

• RG Noble set up traffic control starting from a point approximately 50 yards north of the Town Center Gateway and Town Center Drive intersection.

• The traffic control extended south through the intersection of Town Center Gateway and continued down to the intersection of Nobel Drive and Town Center Drive.

• The outside lanes were closed for both northbound and southbound traffic.

• Traffic was shifted into the number one lanes in both directions.

• **WORK DESCRIPTION:**

• R.J. Noble began work on the southbound side of the road at Town Center Gateway, starting at the south edge of the intersection.

• The crew performed a grind and overlay on the outside lanes, which included the number two lane, turn pockets, and adjacent side streets.

• Work proceeded to the Nobel and Town Center intersection, where paving continued until it met the edge of the previous paving limits at the crosswalk.

• Following the completion of the southbound lanes, crews shifted traffic control to the northbound side of the road.

• A grind and overlay was then performed on the northbound lanes, with work progressing back up to the Town Center Gateway intersection.

• Paving operations were completed at 3:30 AM.

• The contractor performed street sweeping, and all traffic control was picked up by 4:30 AM.

• The shift concluded at 4:30 AM.

• Quality Firm and Kleinfelder were on site to perform compaction testing throughout the night.

Concrete encountered: to be updated

Hours: 7:30 PM - 5:00 AM

Manpower:

LL-02- Foreman - QTY 2 - 9.5 HRS EA - OHLA

LL-04- Operator - QTY 13 - 9.5 HRS EA - OHLA

LL-03- Laborers - QTY 8 - 9.5 HRS EA - OHLA

LL-11- Teamster - QTY 8 - 8.8 HRS EA - DIII, SD GOLD

LL-03- Laborers - QTY 2 - 10 HRS EA - OHLA

LL-11- Teamster - QTY 22 - 9 HRS EA - DIII

LL-04- Operator - QTY 2 - 9 HRS EA - PRSI

Equipment:

LE-113- McElroy Tracstar 16-inch Fusion Machine - QTY 1 - 9.5 HRS EA - OHLA

LE-13- Roller H222 - QTY 2 - 9.5 HRS EA - OHLA

LE-09- Skip Loader - QTY 1 - 9.5 HRS EA - OHLA

LE-125- Skid Steer - QTY 1 - 9.5 HRS EA - OHLA

LE-160- Pup Roller - QTY 1 - 9.5 HRS EA - OHLA

LE-63- Asphalt Paver - QTY 2 - 9.5 HRS EA - OHLA

LE-51- Pickup Truck - QTY 5 - 9.5 HRS EA - OHLA

LE-19- Street sweeper - QTY 2 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 8 - 8.8 HRS EA - DIII, SD GOLD

LL-03- Laborers - QTY 3 - 9.5 HRS EA - OHLA - RENTAL

LE-42- Utility Truck - QTY 1 - 9.5 HRS EA - OHLA

LE-01- Crew Truck - QTY 22 - 9 HRS EA - DIII

LE-71- Pavement Grinder - QTY 2 - 9 HRS EA - PRSI

## Consolidated Resources

| Resource | Pay Type | Class | Qty | Company | Total Hours |
| --- | --- | --- | --- | --- | --- |
| LL-02- Foreman | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 16 |
| LL-02- Foreman | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 3 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 13 | OHL NA | 104 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 13 | OHL NA | 19.5 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 10 | OHL NA | 80 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 8 | OHL NA | 12 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 8 | DIII, SD GOLD | 64 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 8 | DIII, SD GOLD | 6.4 |
| LL-03- Laborers | CS - Cost | LO - Labor Overtime | 2 | OHL NA | 4 |
| LL-11- Teamster | CS - Cost | LR - Labor Regular Time | 22 | DIII | 176 |
| LL-11- Teamster | CS - Cost | LO - Labor Overtime | 22 | DIII | 22 |
| LL-04- Operator | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 16 |
| LL-04- Operator | CS - Cost | LO - Labor Overtime | 2 | PRSI | 2 |
| LE-113- McElroy Tracstar 16-inch Fusion Machine | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-13- Roller H222 | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-09- Skip Loader | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-125- Skid Steer | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-160- Pup Roller | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-63- Asphalt Paver | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-51- Pickup Truck | CS - Cost | LR - Labor Regular Time | 5 | OHL NA | 47.5 |
| LE-19- Street sweeper | CS - Cost | LR - Labor Regular Time | 2 | OHL NA | 19 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 8 | DIII, SD GOLD | 70.4 |
| LL-03- Laborers | CS - Cost | LR - Labor Regular Time | 3 | OHL NA | 28.5 |
| LE-42- Utility Truck | CS - Cost | LR - Labor Regular Time | 1 | OHL NA | 9.5 |
| LE-01- Crew Truck | CS - Cost | LR - Labor Regular Time | 22 | DIII | 198 |
| LE-71- Pavement Grinder | CS - Cost | LR - Labor Regular Time | 2 | PRSI | 18 |